## Findings
ID | Area | Issue | Severity | Impact | Recommended Fix | Owner / Next Step | Status
F1 | Mode/Safety | System is in SYSTEM_MODE=TEST with SEND_ENABLED=FALSE. Master switch — by design it blanks every candidate recipient (actualRecipient_ returns '') and prevents real sends. | Critical | No candidate-facing email actually goes out, so candidates never receive invites/links and never submit forms. Many 'empty tabs' are a downstream symptom of this, not separate bugs. Nothing on screen tells Travis the system is intentionally muted. | Treat TEST/SEND_ENABLED=FALSE as the intended pre-launch state. Add a bright Dashboard banner: 'TEST MODE — no candidate emails are sending.' Only flip to LIVE + SEND_ENABLED=TRUE after queue recovery (F2) is in place. | Travis (go-live) + dev (banner) | Open
F2 | Email Queue | 45 queue rows are BLOCKED and never auto-recover; 25 have a blank 'To (Actual)' baked in at queue time. Flush only processes Status=PENDING and never flips BLOCKED back. 2 rows stuck PENDING. | Critical | Any email queued while SEND_ENABLED=FALSE becomes permanently BLOCKED. Even after going LIVE those candidates are never emailed. Digest counts only PENDING, so 45 BLOCKED show as '0 pending' — zero visibility. | Add a recovery that flips eligible BLOCKED->PENDING and recomputes 'To (Actual)' at SEND time. In _sendQueueRow_, call actualRecipient_(intended) at send, not queue time. Add BLOCKED count to digest. | Dev | Open
F3 | Email Queue | flushEmailQueue runs once/day (everyDays(1).atHour 7) and caps at MAX_PER_FLUSH=50. Every other poller runs every 15-30 min. | Critical | Delayed/quiet-hour/future-dated emails (e.g. 5-day rejection delays) wait up to 24h; a backlog cannot drain. With F2, the queue is effectively stuck. | Reinstall flushEmailQueue on everyMinutes(15). It is lock-guarded and capped, so frequent runs are safe and clear backlogs. | Dev | Open
F4 | Risk Detection | 'Risk Flags' tab empty. Its only writer (runDeterministicRiskReview / applyDeterministicBackstop_) is on a MANUAL menu item only — not any trigger. The automated scoring path intentionally calls a non-writing hook. | Critical | The whole risk/misrepresentation audit trail is blank. Risk is computed but never recorded, so the 'don't auto-book risky candidates' safety net leaves no evidence. | Add a time trigger for runDeterministicRiskReview, OR factor the append into writeRiskFlagsRow_() and call inline from scorePreScreen_ after getDeterministicSignals_. | Dev | Open
F5 | AI Grading | GEMINI_API_KEY missing/blank in Config while AI_GRADING_ENABLED=TRUE and AI_PROVIDER=gemini. 'AI Assessment Results' has only 2 rows. | Critical | If the key isn't actually in Script Properties, every AI grade returns PARSE_FAIL and assessment/transcript scoring is silently degraded; AI tabs stay near-empty. | Confirm GEMINI_API_KEY is in Script Properties (not just the sheet). Add a health-check that fails LOUD if AI enabled but no key/credit. Check if the 2 rows are OK or PARSE_FAIL. | Travis (key) + dev | Open
F6 | Transcripts | 'Transcript Inbox' and 'Ingested Sources Log' empty because all 3 'Transcript Sources' rows have Active=FALSE (Fathom, Otter, Drive). | High | The Gmail/Drive importer fires every 30 min and processes zero rows. No transcripts auto-ingested or graded via this path. | Set one source Active=TRUE with its Gmail Query or Drive Folder ID and Modality. Verify via 'Ingested Sources Log'. Pick ONE path (see F20). | Travis | Open
F7 | Forms | 'Form Responses 1' (Culture form) empty. Populated by Google Forms, not script — empty means the form isn't linked to THIS sheet, or no submissions (expected while emails muted, F1). | High | Culture-fit scoring has no inputs; onCultureSubmit can't run; Interview Pipeline culture scores never populate. | Culture form -> Responses -> Link to Sheets -> point at THIS spreadsheet. Confirm tab name matches Form Registry 'Response Tab'. Submit a live test after go-live. | Travis | Open
F8 | Batch Jobs | Heavy steps in FIX_runEverything defer 'out of time budget' (5-min budget vs 6-min Apps Script limit) and never auto-resume. Fix Everything Log shows 3 deferred (resume grades, recover auto-rejected, dedup/purge). | High | Backfills/recovery silently never finish unless Travis re-clicks. Wrongly auto-rejected candidates may stay rejected. | When deferred>0, create a one-shot ~1-min trigger to re-invoke FIX_runEverything until deferred==0 (self-delete). Or move heavy backfills to their own recurring triggers. | Dev | Open
F9 | Monitoring | CRITICAL error email alerts are gated behind SEND_ENABLED (_maybeAlertCritical_ returns early if sending off). | High | During the periods most likely to be broken (kill switch off / pre-launch), critical alerts are suppressed; failures pile up unseen in the Error Log. | Send internal CRITICAL alerts regardless of SEND_ENABLED. Add a health check that ERROR_ALERT_RECIPIENTS is set. | Dev | Open
F10 | Monitoring | 'Trigger Health' shows Last Fired=(none) for all 14 triggers though triggers clearly fired (174 sent, 5000+ events). It's a static audit, not a live heartbeat. | High | False confidence: every trigger reads 'OK' with no real last-fired data, so a dead trigger looks identical to a healthy one. | Have each handler stamp its own Last Fired/Last Status. Health check should assert the FULL expected trigger set is installed (incl. flushEmailQueue, gradePendingTranscripts, pollCalendarBookings). | Dev | Open
F11 | Audit Trail | 'Override Log' empty; the manager dropdown (onPipelineEdit -> _setBothStatuses_) never logs decisions. Only a manual menu action writes here. | High | Routine hiring decisions (advance/reject/drawer/working interview) leave almost no audit trail — accountability gap. | Have _setBothStatuses_ also call logOverride_({...}) for every dropdown-driven status change. | Dev | Open
F12 | Transcripts | Otter short-transcript rows marked SKIPPED with no Error Log entry, never reprocessed; AI parse-failures retry forever with no digest surfacing. | High | Short/truncated transcripts dropped silently; perpetually-failing ones loop invisibly. Neither reaches Travis. | Route SKIPPED/short and repeatedly-failing transcripts to a visible review surface + digest section; add a failure counter. | Dev | Open
F13 | Config | EMAIL_QUEUE_ENABLED missing from Config (runs on code default). DETERMINISTIC_BACKSTOP_ENABLED / TRANSCRIPT_SOURCES_IMPORT_ENABLED / ASSESSMENT_AUTO_RUN_ENABLED also rely on code defaults, not explicit rows. | High | Behavior depends on invisible code defaults; a future default change silently alters live behavior. | Add every flag the code reads as an explicit Config row with its value. Never rely on defaults for sending or major subsystems. | Dev | Open
F14 | Config | Config drift: an 'OLD Config' tab and a 'Config [WITH DRIFT — reference only]' tab exist alongside the live Config. | Medium | Multiple config copies invite editing the wrong one and reintroducing stale values — recurring 'why did it change' confusion. | Reconcile to ONE Config as single source of truth. Export OLD/DRIFT to an archive file and delete from the live workbook. | Dev | Open
F15 | Silent Skips | Several flag gates return silently with no log when off (e.g. AUTO_BOOKING_ENABLED=FALSE skips booking email; rejection sub-gates). | Medium | A candidate who should get a booking link or rejection gets nothing, with no record of why — reads as silent failure. | logEvent_ on each skip so Event Log/digest shows why an expected email didn't send. | Dev | Open
F16 | Data Integrity | appendRowByHeader_ silently drops unknown keys and fills missing columns with '' — errors only if zero header rows. | Medium | Any future header rename loses that column's data with no error — fragile against routine sheet edits. | Log a WARN listing dropped keys; consider failing loud on schema mismatch for critical tabs. | Dev | Open
F17 | Digest | DIGEST_sendNow sends directly via GmailApp, bypassing queue, dedup ledger, and TEST-mode rerouting. | Medium | Breaks the 'every send goes through the queue' doctrine; in TEST mode emails the real manager (low candidate risk, internal mail). | Route the digest via queueEmail_ with an internal template key, or at minimum honor actualRecipient_. | Dev | Open
F18 | Throughput | Per-run caps of 25 (Otter intake, grading, source import) have no 'rows still pending after cap' alert. | Medium | On a burst, a backlog accumulates quietly and the manager never learns it's falling behind. | On hitting the cap with rows remaining, log a WARN and surface backlog count in the digest. | Dev | Open
F19 | Complexity | Over-built for one shop: 18,661 lines, 495 functions, 45 tabs, 171 Config keys, 13 triggers, ~55 menu items, 15+ subsystems. Lean single-shop build is ~3-4k lines, ~5 tabs, 1 form-submit + ~2 triggers, ~40 keys. | High | Operational fragility and maintenance burden one GM cannot realistically own. More surface area = more silent ways to break — the root of the current symptoms. | Adopt the consolidation plan (F20-F24); target ~80% reduction with the same real-world outcome. | Travis decision + dev | Open
F20 | Complexity | Redundant engines: TWO risk engines (AI 06 + deterministic 33); FIVE AI scoring paths (prescreen/resume/transcript/assessment/culture) + 2 meta-engines; FIVE transcript ingestion paths. | High | Each duplicate is another thing to configure, break, and reconcile; multiple scores answer the same 'is this person qualified' question. | Pick ONE risk approach (keep cheap, explainable deterministic). Collapse AI scoring to 1-2 (one fit score + optional interview score). Pick ONE transcript path (Fathom OR Otter). | Travis decision + dev | Open
F21 | Complexity | 11 log/audit tabs (Error, Event, Notification, AI Grading, Override, Assessment Audit, Daily Digest, Ingested Sources, Email Ledger, Setup Registry ~2,472 rows, Trigger Health). | Medium | Observability built for an on-call team, for one user. Setup Registry alone is 2,472 rows of noise. | Collapse to ~2: one Error/Event log + one Email ledger. Archive/clear Setup Registry. | Dev | Open
F22 | Complexity | Resident repair/scaffolding in production: 23_Backfill (1,241 ln), 40_Fix_Everything, 28_Pipeline_Dedup, 39_Pipeline_Cleanup, 26_Interview_Worksheets (1,744 ln), 20_Smoke_Tests, 32_Instruction_Manual, 99_Export_Source. | Medium | A 'Fix Everything' button + a backfill engine to 'recover wrongly auto-rejected candidates' imply the system breaks often enough to need them — complexity creating complexity. | Move one-time repair/migration and dev scaffolding to a separate dev project. With one intake path + one candidate store, dedup/backfill largely stop being needed. | Dev | Open
F23 | Complexity | 13 polling triggers (15/30/60 min) on free Apps Script quota, for a shop getting a few applicants a day. | Medium | Burns quota and multiplies failure points for negligible benefit. | Cut toward ~3 triggers: 1 form-submit, 1 frequent queue flush (F3), 1 daily digest. Fold pollers into the daily run. | Dev | Open
F24 | Best Practice | Design defaults to fail-SILENT (safeRun_ + ~150 try/catch swallowing to tabs nobody reads); scoring/threshold logic lives in script not visible sheet formulas. | High | For a single operator, silent failure is more dangerous than a visible crash — the system quietly stops and nobody notices (the reported symptom). | Shift to fail-LOUD: surface failures to digest/email immediately. Move score thresholds/gates into sheet formulas Travis can see and adjust. | Dev | Open
F25 | Not a bug | 'Backfill Review Queue', 'Backfill Transcripts' are manual input tabs; 'Transcript Inbox' only fills with unmatched items. | Info | Empty is the correct resting state — do NOT chase them as failures (Risk Flags is the exception, see F4). | No action. Documented so they aren't mistaken for broken. | Closed - by design

## Live Snapshot
RECRUITING OS — LIVE SNAPSHOT (export 2026-06-16; live modified 2026-06-19)
Key safety / config settings (live Config tab)
SYSTEM_MODE | TEST
SEND_ENABLED | FALSE
EMAIL_QUEUE_ENABLED | MISSING from Config
EMAIL_QUEUE_FLUSH_HOUR | 7 (once per day)
QUIET_HOURS | ENABLED 07:00-21:00
GEMINI_API_KEY | MISSING/blank in Config
AI_GRADING_ENABLED | TRUE
AI_PROVIDER | gemini
AUTO_BOOKING_ENABLED | FALSE
AUTO_REJECTION_ENABLED | TRUE
DAILY_DIGEST_TIME | 15:30
TEST_RECIPIENT_EMAIL | travis.burd@frankseuropeanservice.com
ERROR_ALERT_RECIPIENTS | travis.burd@frankseuropeanservice.com
Email Queue status (247 rows)
SENT | 174
BLOCKED | 45
CANCELLED | 26
PENDING | 2
Blank 'To (Actual)' | 25
Empty / under-filled tabs of concern
Risk Flags | 0
Transcript Inbox | 0
Ingested Sources Log | 0
Override Log | 0
Form Responses 1 (Culture) | 0
AI Assessment Results | 2
Transcript Sources Active rows | 0
Scale (single shop)
Lines of code | 18661
Functions | 495
Spreadsheet tabs | 45
Config keys | 171
Installed triggers | 13
Menu items | ~55
Lean target | ~3-4k lines / ~5 tabs / ~3 triggers / ~40 keys